## Petunjuk
ANALISA JAM ALAT DAN KEBUTUHAN MATERIAL
Basis: rekomendasi ruas pada workbook sumber dan SE-DJBK No. 68/2024 Lampiran IV SDA.
Formula produktivitas Bulldozer mengikuti contoh PDF/gambar: q=L x H^2; Ts=(L2x60/VF)+(L2x60/VR)+T3; Q=q x Fb x Fm x Fa x 60/(Ts x 60); koefisien=1/Q.
Kode pekerjaan: GRD Grading, RIP Ripping, SPR Spreading, CMP Compacting, DRN Drainase, SUB Perbaikan tanah dasar, BSC Basecourse baru, PTH Patching lubang, SEM Semenisasi.
Kode alat: AL-DZR Dozer/Bulldozer, AL-GRD Motor Grader, AL-RLR Roller/Compactor, AL-EXC Excavator, AL-WTR Water Tanker.
Sel input pada sheet Asumsi dapat diganti. Semua jam, biaya, dan material pada sheet analisa menggunakan formula antar-sheet.
Ruas kondisi baik tanpa rekomendasi tidak dihitung.

## Asumsi
PARAMETER GEOMETRIK DAN MATERIAL
Parameter | Nilai | Satuan | Keterangan
Lebar jalan JU | 5 | m | Input lapangan
Lebar jalan JP | 4 | m | Input lapangan
Tebal olah ripping/compact | 0.15 | m | Input spesifikasi
Tebal basecourse baru | 0.2 | m | Input spesifikasi
Lebar efektif drainase | 0.5 | m | Asumsi penampang
Kedalaman efektif drainase | 0.4 | m | Asumsi penampang
Air pemadatan | 0.05 | m3/m3 | Input kadar air
PARAMETER FORMULA BULLDOZER - SE-DJBK 68/2024 LAMPIRAN IV
Parameter | Nilai | Satuan | Keterangan
Lebar pisau L | 3.175 | m | Contoh PDF/gambar
Tinggi pisau H | 1.3 | m | Contoh PDF/gambar
Faktor pisau Fb | 1 | - | Tabel faktor
Faktor kemiringan Fm | 1 | - | Gambar faktor
Faktor efisiensi Fa | 0.83 | - | Tabel efisiensi
Kecepatan maju VF | 3.4 | km/jam | Contoh PDF/gambar
Kecepatan mundur VR | 6.97 | km/jam | Contoh PDF/gambar
Jarak penggusuran L2 | 100 | m | Contoh PDF/gambar
Waktu tetap T3 | 0.1 | menit | Contoh PDF/gambar
Kapasitas pisau q |  | m3 | q=L x H^2
Waktu gusur T1 |  | menit | T1=(L2x60)/VF
Waktu kembali T2 |  | menit | T2=(L2x60)/VR
Waktu siklus Ts |  | menit | Ts=T1+T2+T3
Kapasitas produksi Q |  | m3/jam | Q=q x Fb x Fm x Fa x 60/Ts
Koefisien Dozer |  | jam/m3 | 1/Q
PARAMETER ALAT DAN BIAYA OPERASI
Kode alat | Nama alat | Harga pokok | Nilai sisa | Umur (th) | Jam/tahun | Bunga | Asuransi | Daya kW | BBM l/jam | Harga BBM | Pelumas/l | Bengkel | Perbaikan | Operator | Upah/jam | Produktivitas m2/jam | Produktivitas m3/jam | Biaya alat/jam
AL-GRD | Motor Grader | 1800000000 | 0.1 | 8 | 1600 | 0.1 | 0.02 | 130 | 15 | 15000 | 18000 | 0.025 | 0.075 | 1 | 35000 | 3000 | 90
AL-DZR | Bulldozer 155 HP | 2500000000 | 0.1 | 8 | 1600 | 0.1 | 0.02 | 150 | 20 | 15000 | 18000 | 0.025 | 0.075 | 1 | 35000 | 2500 | 110
AL-RLR | Vibro/Tire Roller | 1400000000 | 0.1 | 8 | 1600 | 0.1 | 0.02 | 100 | 12 | 15000 | 18000 | 0.025 | 0.075 | 1 | 35000 | 2200 | 75
AL-EXC | Excavator | 2200000000 | 0.1 | 8 | 1600 | 0.1 | 0.02 | 120 | 16 | 15000 | 18000 | 0.025 | 0.075 | 1 | 35000 | 1800 | 60
AL-WTR | Water Tanker | 900000000 | 0.1 | 8 | 1600 | 0.1 | 0.02 | 100 | 10 | 15000 | 18000 | 0.025 | 0.075 | 1 | 35000 | 2000 | 50
PARAMETER PRODUKTIVITAS PEKERJAAN - SE-DJBK 68/2024
Parameter | Nilai | Satuan | Keterangan
Lebar kerja grader | 3.7 | m | Lebar efektif lintasan
Kecepatan kerja grader | 4 | km/jam | Kecepatan kerja efektif
Efisiensi grader | 0.75 | - | Faktor efisiensi kerja
Lintasan roller | 6 | lintasan | Lintasan pemadatan
Lebar efektif roller | 2.1 | m | Lebar drum efektif
Kecepatan roller | 3 | km/jam | Kecepatan pemadatan
Efisiensi roller | 0.8 | - | Faktor efisiensi kerja
Kapasitas bucket excavator | 0.8 | m3 | Kapasitas bucket
Faktor isi bucket | 0.85 | - | Faktor isi material
Efisiensi excavator | 0.83 | - | Faktor efisiensi kerja
Waktu siklus excavator | 0.5 | menit | Waktu gali-muat-buang
Koefisien semen semenisasi | 0.35 | zak/m2 | Input spesifikasi pekerjaan
Koefisien pasir semenisasi | 0.06 | m3/m2 | Input spesifikasi pekerjaan
Koefisien air semenisasi | 0.015 | m3/m2 | Input spesifikasi pekerjaan

## Kode_Pekerjaan
Kode | Jenis pekerjaan | Satuan | Alat/tenaga | Kode alat yang dihitung | Kode analisa SE-DJBK | Uraian acuan | Dasar produktivitas
GRD | Grading/perataan | m2 | AL-GRD | AL-GRD | A.3.02 | Perataan/pembentukan badan jalan | Luas / Q grader
RIP | Ripping/penggemburan | m3 | AL-DZR | AL-DZR | A.3.02 | Penggemburan lapisan existing | Volume / Q dozer
SPR | Spreading/penyebaran | m3 | AL-DZR + AL-GRD | AL-DZR,AL-GRD | A.3.02 | Penyebaran dan pembentukan material | Volume / Q alat
CMP | Compacting/pemadatan | m3 | AL-RLR + AL-WTR | AL-RLR,AL-WTR | A.3.03 | Pemadatan dengan pengaturan kadar air | Volume / Q roller; air / kapasitas tanker
DRN | Drainase/galian | m3 | AL-EXC | AL-EXC | A.3.01.1a | Galian tanah dan galian batu | Volume galian / Q excavator
SUB | Perbaikan tanah dasar | m3 | AL-EXC + AL-DZR + AL-GRD + AL-RLR + AL-WTR | AL-EXC,AL-DZR,AL-GRD,AL-RLR,AL-WTR | A.3.01.1a | Striping Top Soil, tebas-tebang pohon, dan produktivitas excavator | Volume / Q masing-masing alat
BSC | Basecourse baru | m3 | AL-DZR + AL-GRD + AL-RLR + AL-WTR | AL-DZR,AL-GRD,AL-RLR,AL-WTR | A.3.04 | Penghamparan, pembentukan, pembasahan, dan pemadatan basecourse | Volume / Q masing-masing alat
PTH | Patching lubang | m3 | AL-EXC + AL-GRD + AL-RLR + AL-WTR | AL-EXC,AL-GRD,AL-RLR,AL-WTR | A.3.05 | Perbaikan lokal lubang dan pemadatan | Volume / Q masing-masing alat
SEM | Semenisasi | m2 | MAN | MAN | A.3.06 | Pekerjaan manual semenisasi | Material dan tenaga manual

## Kode_Alat
Kode alat | Nama alat | Keterangan
AL-DZR | Bulldozer 155 HP | Ripping, spreading, basecourse
AL-GRD | Motor Grader | Grading
AL-RLR | Vibro/Tire Roller | Compacting
AL-EXC | Excavator | Drainase dan tanah dasar
AL-WTR | Water Tanker | Air pemadatan

## Input_Jalan
No | Afdeling | Kondisi | Titik Kode | Jenis Jalan | Blok | Jenis Kerusakan | Rekomendasi | Panjang m | Lebar m | Luas m2 | WS | LM | CR | UN | PH
1 | AFD 1 | RUSAK SEDANG | RS 1 | JU | A11 | LM30%, CR 70% | RIPPING + SPREADING + COMPACTING + GRADING | 680 |  |  | 0 | 0.3 | 0.7 | 0 | 0
2 | AFD 1 | RUSAK SEDANG | RS 2 | JP | A13 | WS10%, LM40%, CR50% | GRADING + DRAINASE + RIPPING + SPREADING + COMPACTING | 547 |  |  | 0.1 | 0.4 | 0.5 | 0 | 0
3 | AFD 1 | RUSAK SEDANG | RS 3 | JP | A28 | WS20%, CR80% | GRADING + DRAINASE + COMPACTING | 458 |  |  | 0.2 | 0 | 0.8 | 0 | 0
4 | AFD 1 | RUSAK SEDANG | RS 4 | JP | A19 | LM40%, CR60% | RIPPING + SPREADING + COMPACTING + GRADING | 650 |  |  | 0 | 0.4 | 0.6 | 0 | 0
5 | AFD 1 | RUSAK SEDANG | RS 5 | JP | A20 | WS10%, CR90% | GRADING + DRAINASE + COMPACTING | 415 |  |  | 0.1 | 0 | 0.9 | 0 | 0
6 | AFD 1 | RUSAK SEDANG | RS 6 | JP | A30 | LM30%, CR 70% | RIPPING + SPREADING + COMPACTING + GRADING | 529 |  |  | 0 | 0.3 | 0.7 | 0 | 0
27 | AFD 1 | RUSAK SEDANG | RS 27 | JP | A16 | LM30%, CR 70% | RIPPING + SPREADING + COMPACTING + GRADING | 923 |  |  | 0 | 0.3 | 0.7 | 0 | 0
28 | AFD 1 | RUSAK SEDANG | RS 28 | JP | A26 | PH5%, CR80%, WS15% | PATCHING LUBANG + PEMADATAN + GRADING + DRAINASE + COMPACTING | 874 |  |  | 0.15 | 0 | 0.8 | 0 | 0.05
29 | AFD 1 | RUSAK SEDANG | RS 29 | JP | A16 | WS10%, CR90% | GRADING + DRAINASE + COMPACTING | 792 |  |  | 0.1 | 0 | 0.9 | 0 | 0
30 | AFD 1 | RUSAK SEDANG | RS 30 | JP | A3 | LM30%, CR60%, PH10% | RIPPING + SPREADING + COMPACTING + GRADING + PEMADATAN | 667 |  |  | 0 | 0.3 | 0.6 | 0 | 0.1
31 | AFD 1 | RUSAK SEDANG | RS 31 | JP | A23 | LM30%, CR 70% | RIPPING + SPREADING + COMPACTING + GRADING | 622 |  |  | 0 | 0.3 | 0.7 | 0 | 0
32 | AFD 1 | RUSAK SEDANG | RS 32 | JP | A3 | LM40%, CR60% | RIPPING + SPREADING + COMPACTING + GRADING | 561 |  |  | 0 | 0.4 | 0.6 | 0 | 0
33 | AFD 1 | RUSAK SEDANG | RS 33 | JP | A19 | WS10%, LM30%, CR60% | GRADING + DRAINASE + RIPPING + SPREADING + COMPACTING | 554 |  |  | 0.1 | 0.3 | 0.6 | 0 | 0
34 | AFD 1 | RUSAK SEDANG | RS 34 | JP | A6 | WS10%, LM40%, CR50% | GRADING + DRAINASE + RIPPING + SPREADING + COMPACTING | 536 |  |  | 0.1 | 0.4 | 0.5 | 0 | 0
35 | AFD 1 | RUSAK SEDANG | RS 35 | JP | A3 | WS20%, CR80% | GRADING + DRAINASE + COMPACTING | 489 |  |  | 0.2 | 0 | 0.8 | 0 | 0
36 | AFD 1 | RUSAK SEDANG | RS 36 | JP | A11 | LM40%, CR60% | RIPPING + SPREADING + COMPACTING + GRADING | 412 |  |  | 0 | 0.4 | 0.6 | 0 | 0
37 | AFD 1 | RUSAK SEDANG | RS 37 | JP | A24 | WS10%, CR90% | GRADING + DRAINASE + COMPACTING | 312 |  |  | 0.1 | 0 | 0.9 | 0 | 0
38 | AFD 1 | RUSAK SEDANG | RS 38 | JP | A10 | LM30%, CR 70% | RIPPING + SPREADING + COMPACTING + GRADING | 276 |  |  | 0 | 0.3 | 0.7 | 0 | 0
39 | AFD 1 | RUSAK SEDANG | RS 39 | JPN | A30 | WS10%, LM40%, CR50% | GRADING + DRAINASE + RIPPING + SPREADING + COMPACTING | 764 |  |  | 0.1 | 0.4 | 0.5 | 0 | 0
40 | AFD 1 | RUSAK SEDANG | RS 40 | JPN | A14 | WS20%, CR80% | GRADING + DRAINASE + COMPACTING | 380 |  |  | 0.2 | 0 | 0.8 | 0 | 0
41 | AFD 1 | RUSAK SEDANG | RS 41 | JB | A28 | LM40%, CR60% | RIPPING + SPREADING + COMPACTING + GRADING | 1119 |  |  | 0 | 0.4 | 0.6 | 0 | 0
42 | AFD 1 | RUSAK SEDANG | RS 42 | JB | A15 | WS10%, CR90% | GRADING + DRAINASE + COMPACTING | 1088 |  |  | 0.1 | 0 | 0.9 | 0 | 0
43 | AFD 1 | RUSAK SEDANG | RS 43 | JB | A25 | LM30%, CR 70% | RIPPING + SPREADING + COMPACTING + GRADING | 565 |  |  | 0 | 0.3 | 0.7 | 0 | 0
44 | AFD 1 | RUSAK SEDANG | RS 44 | JB | A15 | PH5%, CR80%, WS15% | PATCHING LUBANG + PEMADATAN + GRADING + DRAINASE + COMPACTING | 103 |  |  | 0.15 | 0 | 0.8 | 0 | 0.05
45 | AFD 1 | RUSAK SEDANG | RS 45 | JA | A10-A13 | LM40%, CR60% | RIPPING + SPREADING + COMPACTING + GRADING | 2077 |  |  | 0 | 0.4 | 0.6 | 0 | 0
24 | AFD 1 | RUSAK BERAT | RB 1 | JU | A18 | LM30%, UN30%, CR40% | RIPPING + SPREADING + COMPACTING + PERBAIKAN TANAH DASAR + BASECOURSE BARU + GRADING | 610 |  |  | 0 | 0.3 | 0.4 | 0.3 | 0
25 | AFD 1 | RUSAK BERAT | RB 2 | JU | A2 | LM30%, UN30%, CR40% | RIPPING + SPREADING + COMPACTING + PERBAIKAN TANAH DASAR + BASECOURSE BARU + GRADING | 628 |  |  | 0 | 0.3 | 0.4 | 0.3 | 0
26 | AFD 1 | RUSAK BERAT | RB 3 | JU | A29 | WS20%, LM30%, CR50% | GRADING + DRAINASE + RIPPING + SPREADING + COMPACTING | 484 |  |  | 0.2 | 0.3 | 0.5 | 0 | 0
27 | AFD 1 | RUSAK BERAT | RB 4 | JP | A17 | WS30%, CR70% | GRADING + DRAINASE + COMPACTING | 638 |  |  | 0.3 | 0 | 0.7 | 0 | 0
28 | AFD 1 | RUSAK BERAT | RB 5 | JU | A16 | LM40%, UN30%, CR30% | RIPPING + SPREADING + COMPACTING + PERBAIKAN TANAH DASAR + BASECOURSE BARU + GRADING | 630 |  |  | 0 | 0.4 | 0.3 | 0.3 | 0
29 | AFD 1 | RUSAK BERAT | RB 6 | JU | A25 | WS20%, LM30%, CR50% | GRADING + DRAINASE + RIPPING + SPREADING + COMPACTING | 626 |  |  | 0.2 | 0.3 | 0.5 | 0 | 0
30 | AFD 1 | RUSAK BERAT | RB 7 | JU | A23 | LM50%, UN20%, CR30% | RIPPING + SPREADING + COMPACTING + PERBAIKAN TANAH DASAR + BASECOURSE BARU + GRADING | 685 |  |  | 0 | 0.5 | 0.3 | 0.2 | 0
31 | AFD 1 | RUSAK BERAT | RB 8 | JU | A7 | LM50%, CR50% | RIPPING + SPREADING + COMPACTING + GRADING | 1358 |  |  | 0 | 0.5 | 0.5 | 0 | 0
32 | AFD 1 | RUSAK BERAT | RB 9 | JU | A3 | WS20%, LM30%, CR50% | GRADING + DRAINASE + RIPPING + SPREADING + COMPACTING | 974 |  |  | 0.2 | 0.3 | 0.5 | 0 | 0
33 | AFD 1 | RUSAK BERAT | RB 10 | JP | A1 | WS20%, CR80% | GRADING + DRAINASE + COMPACTING | 693 |  |  | 0.2 | 0 | 0.8 | 0 | 0
34 | AFD 1 | RUSAK BERAT | RB 11 | JU | A4 | LM30%, UN30%, CR40% | RIPPING + SPREADING + COMPACTING + PERBAIKAN TANAH DASAR + BASECOURSE BARU + GRADING | 576 |  |  | 0 | 0.3 | 0.4 | 0.3 | 0
35 | AFD 1 | RUSAK BERAT | RB 12 | JP | A27 | LM30%, UN30%, CR40% | RIPPING + SPREADING + COMPACTING + PERBAIKAN TANAH DASAR + BASECOURSE BARU + GRADING | 684 |  |  | 0 | 0.3 | 0.4 | 0.3 | 0
36 | AFD 1 | RUSAK BERAT | RB 13 | JP | A3 | WS20%, LM30%, CR50% | GRADING + DRAINASE + RIPPING + SPREADING + COMPACTING | 467 |  |  | 0.2 | 0.3 | 0.5 | 0 | 0
37 | AFD 1 | RUSAK BERAT | RB 14 | JPN | A27 | LM40%, UN30%, CR30% | RIPPING + SPREADING + COMPACTING + PERBAIKAN TANAH DASAR + BASECOURSE BARU + GRADING | 491 |  |  | 0 | 0.4 | 0.3 | 0.3 | 0
1 | AFD 2 | RUSAK SEDANG | RS 1 | JP | B5 | LM40%, CR 60% | RIPPING + SPREADING + COMPACTING + GRADING | 628 |  |  | 0 | 0.4 | 0.6 | 0 | 0
2 | AFD 2 | RUSAK SEDANG | RS 2 | JU | B3 | LM50%, CR50% | RIPPING + SPREADING + COMPACTING + GRADING | 575 |  |  | 0 | 0.5 | 0.5 | 0 | 0
3 | AFD 2 | RUSAK SEDANG | RS 3 | JP | B13 | WS10%, LM40%, CR50% | GRADING + DRAINASE + RIPPING + SPREADING + COMPACTING | 1450 |  |  | 0.1 | 0.4 | 0.5 | 0 | 0
4 | AFD 2 | RUSAK SEDANG | RS 4 | JP | B15 | LM50%, CR50% | RIPPING + SPREADING + COMPACTING + GRADING | 430 |  |  | 0 | 0.5 | 0.5 | 0 | 0
5 | AFD 2 | RUSAK SEDANG | RS 5 | JP | B10 | WS10%, CR90% | GRADING + DRAINASE + COMPACTING | 705 |  |  | 0.1 | 0 | 0.9 | 0 | 0
7 | AFD 2 | RUSAK SEDANG | RS 6 | JP | B9 | LM50%, UN50% | RIPPING + SPREADING + COMPACTING + PERBAIKAN TANAH DASAR + BASECOURSE BARU | 565 |  |  | 0 | 0.5 | 0 | 0.5 | 0
1 | AFD 3 | RUSAK SEDANG | RS 1 | JU | C19 | LM50%, UN50% | RIPPING + SPREADING + COMPACTING + PERBAIKAN TANAH DASAR + BASECOURSE BARU | 811 |  |  | 0 | 0.5 | 0 | 0.5 | 0
2 | AFD 3 | RUSAK SEDANG | RS 2 | JU | C17 | LM40%, CR60% | RIPPING + SPREADING + COMPACTING + GRADING | 748 |  |  | 0 | 0.4 | 0.6 | 0 | 0
3 | AFD 3 | RUSAK SEDANG | RS 3 | JU | C8 | LM30%, CR 70% | RIPPING + SPREADING + COMPACTING + GRADING | 637 |  |  | 0 | 0.3 | 0.7 | 0 | 0
4 | AFD 3 | RUSAK SEDANG | RS 4 | JU | C9 | WS10%, LM40%, CR50% | GRADING + DRAINASE + RIPPING + SPREADING + COMPACTING | 520 |  |  | 0.1 | 0.4 | 0.5 | 0 | 0
5 | AFD 3 | RUSAK SEDANG | RS 5 | JU | C21 | WS10%, LM40%, CR50% | GRADING + DRAINASE + RIPPING + SPREADING + COMPACTING | 264 |  |  | 0.1 | 0.4 | 0.5 | 0 | 0
6 | AFD 3 | RUSAK SEDANG | RS 6 | JP | C5 | LM30%, CR 70% | RIPPING + SPREADING + COMPACTING + GRADING | 1340 |  |  | 0 | 0.3 | 0.7 | 0 | 0
17 | AFD 3 | RUSAK BERAT | RB 4 | JP | C21 | WS30%, CR30%, LM40% | GRADING + DRAINASE + COMPACTING + RIPPING + SPREADING | 820 |  |  | 0.3 | 0.4 | 0.3 | 0 | 0
18 | AFD 3 | RUSAK BERAT | RB 5 | JP | C20 | WS20%, CR30%, LM50% | GRADING + DRAINASE + COMPACTING + RIPPING + SPREADING + SEMENISASI | 416 |  |  | 0.2 | 0.5 | 0.3 | 0 | 0
19 | AFD 3 | RUSAK BERAT | RB 6 | JU | C1 | WS20%, CR80% | GRADING + DRAINASE + COMPACTING | 1020 |  |  | 0.2 | 0 | 0.8 | 0 | 0
20 | AFD 3 | RUSAK BERAT | RB 7 | JP | C14 | WS10%, LM30%, CR60% | GRADING + DRAINASE + RIPPING + SPREADING + COMPACTING | 820 |  |  | 0.1 | 0.3 | 0.6 | 0 | 0
21 | AFD 3 | RUSAK BERAT | RB 8 | JU | C16 | LM50%, CR50% | RIPPING + SPREADING + COMPACTING + PERBAIKAN TANAH DASAR + BASECOURSE BARU + GRADING | 606 |  |  | 0 | 0.5 | 0.5 | 0 | 0
22 | AFD 3 | RUSAK BERAT | RB 9 | JU | C13 | WS20%, LM30%, CR50% | RIPPING + SPREADING + COMPACTING + PERBAIKAN TANAH DASAR + BASECOURSE BARU + GRADING | 517 |  |  | 0.2 | 0.3 | 0.5 | 0 | 0
1 | AFD 4 | RUSAK SEDANG | RS 1 | JP | D17 | WS20%, CR80% | GRADING + DRAINASE + COMPACTING | 789 |  |  | 0.2 | 0 | 0.8 | 0 | 0
2 | AFD 4 | RUSAK SEDANG | RS 2 | JP | D14 | WS10%, LM40%, CR50% | GRADING + DRAINASE + RIPPING + SPREADING + COMPACTING | 373 |  |  | 0.1 | 0.4 | 0.5 | 0 | 0
3 | AFD 4 | RUSAK SEDANG | RS 3 | JP | D10 | LM50%, CR50% | RIPPING + SPREADING + COMPACTING + GRADING | 365 |  |  | 0 | 0.5 | 0.5 | 0 | 0
4 | AFD 4 | RUSAK SEDANG | RS 4 | JP | D5 | WS10%, CR90% | GRADING + DRAINASE + COMPACTING | 761 |  |  | 0.1 | 0 | 0.9 | 0 | 0
5 | AFD 4 | RUSAK SEDANG | RS 5 | JU | D4 | LM40%, CR60% | RIPPING + SPREADING + COMPACTING + GRADING | 571 |  |  | 0 | 0.4 | 0.6 | 0 | 0
6 | AFD 4 | RUSAK SEDANG | RS 6 | JP | D11 | LM30%, CR 70% | RIPPING + SPREADING + COMPACTING + GRADING | 405 |  |  | 0 | 0.3 | 0.7 | 0 | 0
1 | AFD 5 | RUSAK SEDANG | RS 1 | JP | E2 | LM50%, UN50% | RIPPING + SPREADING + COMPACTING + PERBAIKAN TANAH DASAR + BASECOURSE BARU | 568 |  |  | 0 | 0.5 | 0 | 0.5 | 0
2 | AFD 5 | RUSAK SEDANG | RS 2 | JP | E1 | LM40%, CR60% | RIPPING + SPREADING + COMPACTING + GRADING | 1048 |  |  | 0 | 0.4 | 0.6 | 0 | 0
3 | AFD 5 | RUSAK SEDANG | RS 3 | JP | E3 | LM30%, CR 70% | RIPPING + SPREADING + COMPACTING + GRADING | 511 |  |  | 0 | 0.3 | 0.7 | 0 | 0
4 | AFD 5 | RUSAK SEDANG | RS 4 | JP | E13 | WS10%, LM40%, CR50% | GRADING + DRAINASE + RIPPING + SPREADING + COMPACTING | 774 |  |  | 0.1 | 0.4 | 0.5 | 0 | 0
5 | AFD 5 | RUSAK SEDANG | RS 5 | JU | E6 | WS10%, CR90% | GRADING + DRAINASE + COMPACTING | 613 |  |  | 0.1 | 0 | 0.9 | 0 | 0
6 | AFD 5 | RUSAK SEDANG | RS 6 | JU | E12 | LM40%, CR 60% | RIPPING + SPREADING + COMPACTING + GRADING | 553 |  |  | 0 | 0.4 | 0.6 | 0 | 0
27 | AFD 5 | RUSAK BERAT | RB 11 | JU | E20 | WS10%, LM40%, CR50% | GRADING + DRAINASE + RIPPING + SPREADING + COMPACTING | 815 |  |  | 0.1 | 0.4 | 0.5 | 0 | 0
28 | AFD 5 | RUSAK BERAT | RB 12 | JU | E14 | LM30%, UN30%, CR40% | RIPPING + SPREADING + COMPACTING + PERBAIKAN TANAH DASAR + BASECOURSE BARU + GRADING | 490 |  |  | 0 | 0.3 | 0.4 | 0.3 | 0
29 | AFD 5 | RUSAK BERAT | RB 13 | JP | E13 | LM50%, CR50% | RIPPING + SPREADING + COMPACTING + GRADING | 542 |  |  | 0 | 0.5 | 0.5 | 0 | 0
30 | AFD 5 | RUSAK BERAT | RB 14 | JP | E1 | WS30%, CR30%, LM40% | GRADING + DRAINASE + COMPACTING + RIPPING + SPREADING + SEMENISASI | 399 |  |  | 0.3 | 0.4 | 0.3 | 0 | 0

## Analisa_Produktivitas
Kode | Jenis pekerjaan | Alat | Formula/parameter | Produktivitas | Satuan | Koefisien jam | Satuan koef. | Kode AHSP | Halaman acuan | Uraian analisa
GRD | Grading/perataan | AL-GRD | Q=L x V x 1.000 x Fa |  | m2/jam |  | jam/m2 | AHSP-SDA-GRD-PROV | Lampiran IV; halaman belum terverifikasi | Perataan/pembentukan badan jalan
RIP | Ripping/penggemburan | AL-DZR | Q Bulldozer SE-DJBK |  | m3/jam |  | jam/m3 | AHSP-SDA-RIP-PROV | Lampiran IV; halaman belum terverifikasi | Penggemburan lapisan existing
SPR | Spreading/penyebaran | AL-DZR | Q Bulldozer SE-DJBK |  | m3/jam |  | jam/m3 | AHSP-SDA-SPR-PROV | Lampiran IV; halaman belum terverifikasi | Penyebaran dan pembentukan material
CMP | Compacting/pemadatan | AL-RLR | Q=L x V x 1.000 x Fa/n |  | m3/jam |  | jam/m3 | AHSP-SDA-CMP-PROV | Lampiran IV; halaman belum terverifikasi | Pemadatan dengan pengaturan kadar air
DRN | Drainase/galian | AL-EXC | Q=Kb x Fb x Fa x 60/Ts |  | m3/jam |  | jam/m3 | A.3.01.1a | Sekitar hal. 324; verifikasi terhadap edisi PDF | Galian tanah dan galian batu
SUB | Perbaikan tanah dasar | AL-EXC | Q excavator SE-DJBK |  | m3/jam |  | jam/m3 | A.3.01.1a | Lampiran IV; cocokkan halaman PDF | Striping Top Soil, tebas-tebang pohon, dan produktivitas excavator
BSC | Basecourse baru | AL-DZR | Q Bulldozer SE-DJBK |  | m3/jam |  | jam/m3 | AHSP-SDA-BSC-PROV | Lampiran IV; halaman belum terverifikasi | Penghamparan material basecourse
PTH | Patching lubang | AL-EXC | Q excavator SE-DJBK |  | m3/jam |  | jam/m3 | AHSP-SDA-PTH-PROV | Lampiran IV; halaman belum terverifikasi | Perbaikan lokal lubang
SEM | Semenisasi | MAN | Pekerjaan manual; alat berat tidak dihitung | 0 | m2/jam | 0 | jam/m2 | AHSP-SDA-SEM-PROV | Lampiran IV; halaman belum terverifikasi | Pekerjaan manual semenisasi

## Analisa_Alat_Pekerjaan
No | Afdeling | Blok | Kode pekerjaan | Uraian pekerjaan | Kode AHSP | Kode alat | Nama alat | Volume dihitung | Produktivitas | Jam alat | Biaya alat Rp | Rumus/trigger
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR
|  |  | GRD | Grading/perataan | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | GRADING; volume / produktivitas AL-GRD
|  |  | RIP | Ripping/penggemburan | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | RIPPING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-DZR | Bulldozer 155 HP |  |  |  |  | SPREADING; volume / produktivitas AL-DZR
|  |  | SPR | Spreading/penyebaran | A.3.02 | AL-GRD | Motor Grader |  |  |  |  | SPREADING; volume / produktivitas AL-GRD
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-RLR | Vibro/Tire Roller |  |  |  |  | COMPACTING; volume / produktivitas AL-RLR
|  |  | CMP | Compacting/pemadatan | A.3.03 | AL-WTR | Water Tanker |  |  |  |  | COMPACTING; volume / produktivitas AL-WTR
|  |  | DRN | Drainase/galian | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | DRAINASE; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-EXC | Excavator |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-EXC
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-DZR | Bulldozer 155 HP |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-DZR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-GRD | Motor Grader |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-GRD
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-RLR | Vibro/Tire Roller |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-RLR
|  |  | SUB | Perbaikan tanah dasar | A.3.01.1a | AL-WTR | Water Tanker |  |  |  |  | PERBAIKAN TANAH DASAR; volume / produktivitas AL-WTR
|  |  | BSC | Basecourse baru | A.3.04 | AL-DZR | Bulldozer 155 HP |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-DZR
|  |  | BSC | Basecourse baru | A.3.04 | AL-GRD | Motor Grader |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-GRD
|  |  | BSC | Basecourse baru | A.3.04 | AL-RLR | Vibro/Tire Roller |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-RLR
|  |  | BSC | Basecourse baru | A.3.04 | AL-WTR | Water Tanker |  |  |  |  | BASECOURSE BARU; volume / produktivitas AL-WTR
|  |  | PTH | Patching lubang | A.3.05 | AL-EXC | Excavator |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-EXC
|  |  | PTH | Patching lubang | A.3.05 | AL-GRD | Motor Grader |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-GRD
|  |  | PTH | Patching lubang | A.3.05 | AL-RLR | Vibro/Tire Roller |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-RLR
|  |  | PTH | Patching lubang | A.3.05 | AL-WTR | Water Tanker |  |  |  |  | PATCHING LUBANG; volume / produktivitas AL-WTR

## Analisa_Jam_Alat
No | Afdeling | Blok | Panjang m | Luas m2 | Vol olah m3 | Vol drainase m3 | Jam GRD | Jam DZR | Jam RLR | Jam EXC | Jam WTR | Total jam | Biaya alat Rp | Kode pekerjaan terdeteksi | Kode alat

## Kebutuhan_Material
No | Afdeling | Blok | Panjang m | Luas m2 | Existing diolah m3 | Basecourse baru m3 | Air pemadatan m3 | Drainase/galian m3 | Semen zak | Pasir m3 | Air semenisasi m3 | Kode material | Pekerjaan
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM
MAT-EXC / MAT-BSC / MAT-WTR / MAT-SEM

## Referensi_AHSP
Kode analisa | Uraian pekerjaan | Kode AHSP | Alat/tenaga | Dasar perhitungan jam alat | Halaman PDF | Status
GRD | Grading/perataan | AHSP-SDA-GRD-PROV | AL-GRD | Luas / produktivitas grader | Belum terverifikasi | Kode internal sementara
RIP | Ripping/penggemburan | AHSP-SDA-RIP-PROV | AL-DZR | Volume / Q dozer | Belum terverifikasi | Kode internal sementara
SPR | Spreading/penyebaran | AHSP-SDA-SPR-PROV | AL-DZR | Volume / Q dozer | Belum terverifikasi | Kode internal sementara
CMP | Compacting/pemadatan | AHSP-SDA-CMP-PROV | AL-RLR + AL-WTR | Volume / Q roller; air dihitung terpisah | Belum terverifikasi | Kode internal sementara
DRN | Drainase/galian | A.3.01.1a | AL-EXC | Volume galian / Q excavator | Sekitar 324 | Perlu dicocokkan dengan PDF sumber
SUB | Perbaikan tanah dasar / Striping Top Soil | A.3.01.1a | AL-EXC + AL-DZR + AL-GRD + AL-RLR + AL-WTR | Volume / Q excavator, dozer, grader, roller, tanker | Cocokkan PDF | Kode analisa mengacu contoh pengguna
BSC | Basecourse baru | AHSP-SDA-BSC-PROV | AL-DZR + AL-RLR | Volume basecourse / produktivitas pekerjaan | Belum terverifikasi | Kode internal sementara
PTH | Patching lubang | AHSP-SDA-PTH-PROV | AL-EXC | Volume patching / Q excavator | Belum terverifikasi | Kode internal sementara
SEM | Semenisasi | AHSP-SDA-SEM-PROV | Tenaga manual | Tidak ada jam alat berat pada model ini | Belum terverifikasi | Kode internal sementara
Catatan penting
Nomor halaman resmi selain rujukan contoh galian belum diisi karena file PDF SE-DJBK No. 68/2024 Lampiran IV tidak tersedia di workspace saat workbook dibuat.
Kode AHSP-SDA-*-PROV adalah kode internal analisa, bukan nomor item resmi. Ganti setelah PDF sumber dan edisi halaman dikonfirmasi.